## Slide 1
FAIRSHARE SPRINT - 3
KHUSHI SHAH

## Slide 2
SPRINT 1: STORIES
01
02
USER SIGNUP & LOGIN
CREATE GROUP
03
JOIN GROUP VIA INVITE CODE
04
05
ADD EXPENSE
EDIT/DELETE EXPENSE
06
EQUAL EXPENSE SPLIT
07
BASIC BALANCE DASHBOARD
TOTAL STORY POINTS: 37

## Slide 3
SPRINT 2: STORIES
01
SELECT PARTICIPANTS FOR AN EXPENSE
02
PERCENTAGE-BASED EXPENSE SPLIT
03
ATTACH RECEIPTS TO EXPENSES
TOTAL STORY POINTS: 21

## Slide 4
SPRINT 3: STORIES
  Export balance sheet as PDF/CSV
  Includes all:
    Users
    Expenses
    Net balances
  Data matches dashboard
  System generates instructions:
    “A pays B $X”
  Minimizes number of transactions
  Updates balances after settlement
EXPORT BALANCE SHEET (SP: 5)
GENERATE SETTLEMENT PLAN (SP: 8)
  Option to mark all debts as settled
  Resets balances to zero
  Dashboard reflects cleared state
CLEAR ALL DEBTS (SP: 8)
ZELLE INTEGRATION (SP: 5)
  Add Zelle email / phone
  Upload QR code for payments

## Slide 5
SPRINT ESTIMATION &
PROJECT COMPLETION
37
21
26
26
SPRINT 1 VELOCITY
SPRINT 2 VELOCITY
SPRINT 3 VELOCITY
MEDIAN VELOCITY
All planned features successfully completed within 3 sprints, achieving MVP goals with 90% confidence interval reliability.
Total sprints required were 3.
No additional sprint is needed

## Slide 6
TESTING AND COVERAGE
TOOLS (SPRINT 3)
Unit testing framework for backend logic verification
Mocking dependencies including services and repositories
Comprehensive code coverage measurement and reporting
Detect architecture, design and implementation smells
JUNIT 5
MOCKITO
JACOCO
DESIGNITEJAVA
Automated test execution across all test suites
MAVEN SUREFIRE
Frontend logic testing
VITEST
Implemented CI/CD with GitHub Actions to automate testing and ensure consistent code coverage on every push
GITHUB ACTIONS

## Slide 7
  Backend tests were executed using Maven Surefire Plugin.
  A total of 98 automated unit tests were run.
  0 errors, 0 failures, and 0 skipped tests, resulting in a 100% success rate.
  The total test execution time was approximately 4.8 seconds.
  This confirms that the backend functionalities passed all implemented test cases successfully.
  Code coverage was measured using the JaCoCo coverage tool integrated with Maven.
  The backend achieved 61% overall code coverage.
  Controller layer coverage reached 73%, indicating strong API testing.
  Service layer coverage is 52%, reflecting testing of core business logic.
  Model and payload classes achieved 79% and 94% coverage respectively.
  Some configuration and DTO classes remain untested because they mainly contain simple data structures or configuration code.
  Analyzed 1563 LOC, 25 classes, 203 methods using DesigniteJava
  No major architecture smells → system is well-structured
  Minor issues found (long statements, unused abstractions) → scope for improvement
Frontend logic testing was implemented using Vitest. The tests verify UI logic such as user display names, role identification, currency formatting, and invite code validation.
  Github Actions show both successful and unsuccessful builds

## Slide 8
PLANNING BORAD IN GITHUB
SPRINT 1 HAD THE HIGHEST WORKLOAD, FOLLOWED BY A DROP IN SPRINT 2 AND A SLIGHT INCREASE IN SPRINT 3, SHOWING STABILIZED PROGRESS
ALL PLANNED TASKS WERE SUCCESSFULLY COMPLETED, REFLECTING A 100% SPRINT COMPLETION RATE.

## Slide 9
01
02
03
04
05
06
07
REQUIREMENT
GATHERING
SYSTEM DESIGN
SPRINT PLANNING
DEVELOPMENT
CONTINUOUS
INTEGRATION
TESTING
REVIEW &
RETROSPECTIVE
OUR DEVELOPMENT PROCESS
Agile-Based Development Lifecycle
BURNDOWN
CHART
The burndown chart shows steady progress across sprints, with a scope increase in Sprint 3 that was successfully completed within the release.

## Slide 10
KEY METRICS - ALL SPRINTS
•Planned Velocity: 37 points
•Actual Velocity: 37 points
•Sprint Predictability Rate: 100%
•Sprint Addition Rate: 0%
•Sprint Completion Rate: 100%
All actions were kept and evaluated
SPRINT 1
SPRINT 2
SPRINT 3
•Planned Velocity: 21points
•Actual Velocity: 21 points
•Sprint Predictability Rate: 100%
•Sprint Addition Rate: 0%
•Sprint Completion Rate: 100%
All actions were kept and evaluated
•Planned Velocity: 21 points
•Actual Velocity: 26 points
•Sprint Predictability Rate: 81%
•Sprint Addition Rate: 24%
•Sprint Completion Rate: 100%
One additional action was added and evaluated
Overall, Sprint 1 and Sprint 2 demonstrated strong planning accuracy with 100% predictability and completion. In Sprint 3, although predictability decreased due to the addition of a new feature, the team successfully adapted and delivered all planned and additional work. This highlights our ability to balance planning discipline with flexibility, ensuring both consistency and value delivery throughout the project.

## Slide 11
re
SPRINT 3 - RETROSPECTIVE
  Adding new features mid-sprint without buffer planning
  Slight deviation from initial sprint commitment
  Relying more on manual coordination instead of structured tracking
STOP
re
START
re
CONTINUE
  Early discussion before introducing scope changes
  Improving estimation accuracy for dynamic features
  Strengthening communication between frontend & backend
  Completing all committed and additional tasks
  Using CI/CD tools (GitHub Actions, testing pipelines)
  Maintaining transparency through regular updates

## Slide 12
THANK
YOU
DEMONSTRATION: https://youtu.be/GIe5kEu0w4Q